## Logframe
Commercial Agriculture and Resilient Livelihoods Enhancement Programme
Logical Framework
Results Hierarchy | Indicators |  |  |  | Means of Verification |  |  | Assumptions | Project Yr 1 (2015) |  |  | Project Yr 2 (2016) |  |  | Project Yr 3 (2017) |  |  | Project Yr 4 (2018) |  |  | Project Yr 5 (2019) |  |  | Project Yr 6 (2020) |  |  | Project Yr 7 (2021) |  |  | Project Yr 8 (2022) |  |  | Project Yr 9 (2023) |  |  | Project Yr 10 (2024) |  |  | Project Yr 11 (2025) |  |  | Project Yr 10 (2024) |  |  | Project Yr 11 (2025)
| Name | Baseline | Mid-Term | End Target | Source | Frequency | Responsibility |  | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative | Year Targets | Year Results | Cumulative
Outreach | 1.b Estimated corresponding total number of households members |  |  |  | RIMS | Annual
| Household members - Number of people |  | 28975 | 141562 | [8 empty] | 2466 | 2466 |  | 21208 | 23674 | 20000 | 13500 | 37174 |  | 29253 | 66427 | 2000 | 27168 | 93595 | 20000 | 13202 | 106797 | 25000 | 25664 | 132461 |  | 7616 | 140077 |  |  | 140077 |  | 153905 |  |  | 13828 | 153905
| 1.a Corresponding number of households reached |  |  |  | RIMS | Annual | [37 empty] | 0
| Women-headed households - Households |  | 2254 | 14486 | [8 empty] | 246 | 246 |  | 2572 | 2818 |  | 1687 | 4505 |  | 2307 | 6812 |  | 2760 | 9572 |  | 677 | 10249 |  | 3022 | 13271 |  | 904 | 14175 |  |  | 14175 |  | 16015 |  |  | 1840 | 16015
| Non-women-headed households - Households |  | 3382 | 14489 | [8 empty] | 246 | 246 |  | 2572 | 2818 |  | 1688 | 4506 |  | 2307 | 6813 |  | 2900 | 9713 |  | 1264 | 10977 |  | 3394 | 14371 |  | 1000 | 15371 |  |  | 15371 |  | 16988 |  |  | 1617 | 16988
| Households - Households |  | 5636 | 28975 | [7 empty] | 548 | 492 | 492 | 10000 | 5144 | 5636 | 10000 | 3375 | 9011 | 10000 | 4614 | 13625 | 5000 | 5660 | 19285 | 5000 | 1941 | 21226 | 5000 | 6416 | 27642 | 2100 | 1904 | 29546 |  |  | 29546 |  | 33003 |  |  | 3457 | 33003 |  |  |  | 113.9016
| 1 Persons receiving services promoted or supported by the project | [42 empty] | 0
| Males - Males |  |  | 55000 | [8 empty] | 822 | 822 |  | 7200 | 8022 | 5000 | 4500 | 12522 | 6000 | 8751 | 21273 | 5500 | 3982 | 25255 | 5500 | 6745 | 32000 | 5000 | 7951 | 39951 | 8000 | 3616 | 43567 |  |  | 69001 |  | 51115 |  |  | 7548 | 51115
| Females - Females |  | 11088 | 55053 | [8 empty] | 822 | 822 |  | 7069 | 7891 | 5000 | 4500 | 12391 | 6000 | 8751 | 21142 | 5500 | 3644 | 24786 | 5500 | 6457 | 31243 | 5000 | 9455 | 40698 | 8000 | 4000 | 44698 |  |  | 70580 |  | 51441 |  |  | 6743 | 51441
| Young - Young people |  | 200 | 2000 | [8 empty] | 25 | 25 |  | 90 | 115 |  | 5 | 120 |  | 46 | 166 |  | 593 | 759 |  | 250 | 1009 | 500 | 211 | 1220 | 30 | 25 | 1245 |  |  | 1245 |  | 1255 |  |  | 10 | 1255
| Total number of persons receiving services - Number of people |  | 11088 | 110053 | [8 empty] | 1644 | 1644 |  | 14269 | 15913 | 10000 | 9000 | 24913 | 12000 | 17502 | 42415 | 11000 | 7626 | 50041 | 11000 | 13202 | 63243 | 10000 | 17406 | 80649 | 16000 | 7616 | 88265 |  |  | 139581 |  | 102566 |  |  | 14301 | 102566
Project Goal Sustainably increase smallholder producers’ incomes and reduce poverty through commercialization of production within programme households | 5 000 direct beneficiary HH in vegetable and dairy value chains report at least 25% increase in HH asset and income, as compared to baseline (disaggregated by HHs-head gender) |  |  |  | IFAD's Results and Impact Management System (RIMS) and baseline surveys |  |  | No major socio-economic slow down, or natural disasters Increasing support for collaboration between different Agencies, civil society and private sector to develop value chains - Continued MoAF support for innovative approaches Agricultural approaches and technologies primarily remain profitable - Programme investments are realized as designed | [35 empty] | 0
| % of increase in HH asset and income - Percentage (%) |  | 12 | 25 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| 15% reduction in the prevalence of child malnutrition, as compared to baseline |  |  |  | Programme M&E | [38 empty] | 0
| % reduction child malnutrition - Percentage (%) | 31.37 |  | 16.7 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [8 empty] | 0
Development Objective Increased returns to smallholder farmers through climate resilient production of crops and livestock in nationally organized value chains and marketing systems | ≥ 30% increase in production of vegetables and dairy products |  |  |  | Baseline survey - Sector studies - Technical agencies’ reports and studies Research and academic studies Programme M&E |  |  | No major socio-economic slow down, or natural disasters Increasing support for collaboration between different Agencies, civil society and private sector to develop value chains - Continued MoAF support for innovative approaches Agricultural approaches and technologies primarily remain profitable - Programme investments are realized as designed | [35 empty] | 0
| % increase in production - Percentage (%) |  | 25 | 30 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| ≥ 20,000 HH in vulnerable areas with increased water availability for agriculture production |  |  |  | Baseline survey - Sector studies - Technical agencies’ reports and studies Research and academic studies Programme M&E | [38 empty] | 0
| Households - Number |  | 2276 | 20000 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [8 empty] | 0
Outcome Community-based Resilient Agricultural Production has sustainably increased | 6 000 HH adopt sustainable agricultural practices |  |  |  | Programme M&E reports - Contracted studies - RIMS and benchmark - Scientific and conference papers |  |  | Collaboration between Government Agencies/staff and non-state service providers is successful Royal Government of Bhutan (RGoB) complementary financing and supportive annual block grants (dzongkhags) is allocated and utilised | [35 empty] | 0
| Households - Number |  | 5636 | 6000 | [20 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | [7 empty] | 692 | 692
| 1.2.2 Households reporting adoption of new/improved inputs, technologies or practices |  |  |  | RIMS | Annual | OPM | [36 empty] | 0 | [5 empty] | Youth
| Total number of household members - Number of people |  |  | 24000 | [20 empty] | 5000 | 5000 | 5000 | 9511 | 14511 | 5000 | 17190 | 31701 | 6069 | 3400 | 35101 |  |  |  |  | 45769 |  | 12000 | 10668 | 45769 | [5 empty] | Revised target for group formation
| Households - Households |  |  | 6000 | [19 empty] | 4 | 1250 | 1250 | 1500 | 2098 | 3348 | 1500 | 3737 | 7085 | 1200 | 850 | 7935 |  |  |  |  | 10602 |  | 3000 | 2667 | 10602 |  |  |  | 176.7
Output Increased Production Resilience, Diversification and Innovation | ≥ 23 000 (of which 50% are women) smallholder HH supported in coping with the effects of climate change with sustainable land management practices |  |  |  | Base line studies Programme progress report Line agencies’ reports |  |  | RGoB earmarked funding (including other donors) of agricultural inputs and capacity development of farmer groups is allocated and utilised as per programme design - Capacity of Government Agencies/staff and non-state service providers is adequate to achieve results as per programme design | [35 empty] | 0
| Females - Number |  | 1486 | 11500 | [8 empty] | 341 | 341 |  |  | 341 |  |  | 341 |  | 0 | 341 |  | 2178 | 2519 |  | 1111 | 3630 |  | 1259 | 4889 | 1050 | 150 | 5039 |  |  |  |  | 6266 |  | 2750 | 1227 | 6266
| Households - Number |  | 3665 | 23000 | [8 empty] | 345 | 345 |  |  | 345 |  |  | 345 |  | 0 | 345 |  | 3227 | 3572 |  | 1376 | 4948 |  | 2555 | 7503 | 2113 | 210 | 7713 |  |  |  |  | 10444 |  | 5917 | 2731 | 10444
Output Vegetable Production Intensified and Expanded | 300 new vegetable farmer groups (4 500 HH) established and functional; minimum 60% female members |  |  |  | Base line studies Programme progress report Line agencies’ reports |  |  | RGoB earmarked funding (including other donors) of agricultural inputs and capacity development of farmer groups is allocated and utilised as per programme design - Capacity of Government Agencies/staff and non-state service providers is adequate to achieve results as per programme design | [35 empty] | 0
| No. of groups formed - Number |  | 34 | 300 | [16 empty] | 20 | 42 | 42 | 10 | 7 | 49 | 10 | 14 | 63 | 10 | 14 | 77 | 3 | 75 | 152 |  |  |  |  | 152 |  | 0 | 0 | 152
| Policy 1 Policy-relevant knowledge products completed | [42 empty] | 0
| Number - Knowledge Products | [23 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 | 5 | 5 |  |  | 5 |  | 6 |  | 1 | 1 | 6
Output Dairy Production Intensified and Expanded | 150 Smallholder Dairy Farmer Groups (450 HH) established and functional, with minimum 50% female members |  |  |  | Base line studies Programme progress report Line agencies’ reports |  |  | RGoB earmarked funding (including other donors) of agricultural inputs and capacity development of farmer groups is allocated and utilised as per programme design - Capacity of Government Agencies/staff and non-state service providers is adequate to achieve results as per programme design | [35 empty] | 0
| No. of groups formed - Number |  | 21 | 150 | [7 empty] | 10 | 8 | 8 |  |  | 8 |  |  | 8 | 10 | 22 | 30 | 10 | 2 | 32 | 10 | 7 | 39 | 10 | 7 | 46 | 30 | 51 | 97 |  |  |  |  | 100 |  |  | 3 | 100
| Households receiving animals from distribution/restocking |  |  |  | RIMS | Annual | [37 empty] | 0
| Households - Number | [10 empty] | 150 | 100 | 100 |  | 146 | 246 |  | 265 | 511 | 190 | 213 | 724 | 200 | 396 | 1120 | 500 | 472 | 1592 | 200 | 220 | 1812 | 294 | 278 | 2090 |  |  |  |  | 2295 |  | 152 | 205 | 2295
Outcome Increased smallholder income from Crop and Livestock Value Chains | 70% of the agricultural enterprises established have a positive outlook on their profitability and sustainability |  |  |  | Programme M&E reports - RIMS and benchmark -Line agencies’ reports - Sector studies and reports - Farmer satisfaction surveys |  |  | Willingness for collaboration between Government Agencies/staff, FCBL and non-state actors, including small entrepreneurs and businesses, to develop and manage value chains and market infrastructure | [35 empty] | 0
| % of positive outlook on profitability - Percentage (%) |  | 20 | 70 | [20 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
| 2.2.2 Supported rural enterprises reporting an increase in profit |  |  |  | RIMS | Annual | OPM | [36 empty] | 0
| Number of enterprises - Enterprises |  |  | 140 | [8 empty] | 5 | 5 |  | 16 | 21 |  | 12 | 33 |  | 24 | 57 |  | 11 | 68 |  | 32 | 100 | 20 | 16 | 116 | 15 | 30 | 146 |  |  |  |  | 151 |  |  | 5 | 151
| Percentage of enterprises - Percentage (%) | [42 empty] | 0 |  |  |  |  | Endline survey
Output Resilient Vegetable and Dairy Value Chains developed | 65 geogs have developed climate resilient vegetable and dairy production, marketing, and infrastructure management plans |  |  |  | Programme progress report Sector reports and studies |  |  | FCBL has adequate financial allocations to develop its own capacity next to programme support - Geogs are willing to develop more holistic (value chain based) geog plans for dairy and vegetables to guide programme investments and strengthen local institutions for climate resilience | [35 empty] | 0
| No. of geogs - Number |  | 30 | 65 | [11 empty] | 6 | 6 |  |  | 6 | 24 | 24 | 30 |  | 10 | 40 |  | 5 | 45 | 5 | 5 | 50 |  | 0 | 50 |  |  |  |  | 60 |  |  | 10 | 60
Output Agricultural Commercialization and Enterprise Development strengthened | 200 agriculture enterprises (including cooperatives) established and strengthened as part of value chain development |  |  |  | Programme progress report - Sector reports and studies |  |  | Adequate number of interested and able entrepreneurs come forward to establish businesses - Access to finance for small rural agricultural entrepreneurs is adequately facilitated | [35 empty] | 0
| No. of enterprises - Number |  | 34 | 200 | [11 empty] | 3 | 3 |  | 6 | 9 | 20 | 14 | 23 | 10 | 11 | 34 | 10 | 11 | 45 | 20 | 16 | 61 | 15 | 30 | 91 |  |  |  |  | 170 |  |  | 79 | 170 |  |  |  | 85 | Mushroom enterprise-5, oyster mushroom- 59, strawberry-6, poultry farm-1, aggregators-7
| Other productive infrastructure constructed/rehabilitated |  |  |  | RIMS | Annual | [37 empty] | 0
| No. of infrastructure - Number |  | 743 | 1000 | [7 empty] | 35 | 20 | 20 |  | 0 | 20 |  | 60 | 80 |  | 23 | 103 |  | 15 | 118 |  | 50 | 168 | 100 | 171 | 339 | 38 | 34 | 373 |  |  |  |  | 581 |  | 179 | 208 | 581 |  |  |  |  | MCC, MCS, Irrigation, chain link fence, dairy sheds, market shed
| People in groups managing productive infrastructure |  |  |  | RIMS | Annual | [37 empty] | 0
| Males - Number |  |  | 2500 | [8 empty] | 370 | 370 |  | 642 | 1012 |  | 281 | 1293 |  | 565 | 1858 |  | 100 | 1958 |  | 279 | 2237 |  | 173 | 2410 |  | 685 | 3095 |  |  |  |  | 3227 |  |  | 132 | 3227
| Females - Number |  |  | 2000 | [8 empty] | 297 | 297 |  | 264 | 561 |  | 320 | 881 |  | 185 | 1066 |  | 100 | 1166 |  | 344 | 1510 |  | 173 | 1683 |  | 701 | 2384 |  |  |  |  | 2491 |  |  | 107 | 2491
| Groups managing productive infrastructure formed/strengthened |  |  |  | RIMS | Annual | [37 empty] | 0
| No. of groups formed - Number |  | 15 | 30 | [7 empty] | 12 | 15 | 15 |  |  | 15 |  | 2 | 17 |  | 1 | 18 |  | 7 | 25 |  | 7 | 32 | 20 | 14 | 46 |  | 8 | 54 |  |  |  |  | 64 |  |  | 10 | 64
| Crop/Livestock production groups formed/strengthened |  |  |  | RIMS | Annual | [37 empty] | 0
| No. of groups - Number |  |  | 30 | [7 empty] | 10 | 8 | 8 |  | 0 | 8 |  | 0 | 8 |  | 8 | 16 |  | 4 | 20 |  | 7 | 27 | 20 | 7 | 34 |  | 0 | 34 |  |  |  |  | 48 |  |  | 14 | 48
| People trained on land management practices |  |  |  | RIMS | Annual | [37 empty] | 0
| Males - Number |  |  | 1000 | [8 empty] | 146 | 146 |  |  | 146 |  |  | 146 |  | 0 | 146 |  | 250 | 396 | 500 | 0 | 396 |  | 0 | 396 |  | 0 | 396 |  |  |  |  | 687 |  |  | 291 | 687
| Females - Number |  |  | 1000 | [8 empty] | 124 | 124 |  |  | 124 |  |  | 124 |  | 0 | 124 |  | 250 | 374 | 500 | 0 | 374 |  | 0 | 374 |  | 0 | 374 |  |  |  |  | 556 |  |  | 182 | 556
| 2.1.4 Supported rural producers that are members of a rural producers' organization |  |  |  | RIMs survey Impact Assessment Survey MIS | Annual | PMU | [36 empty] | 0
| Total number of persons - Number of people |  |  | 3337 | [8 empty] | 100 | 100 |  |  | 100 |  |  | 100 |  | 0 | 100 |  | 401 | 501 |  | 602 | 1103 |  | 3198 | 4301 |  | 1442 | 5743 |  |  | 5743 |  | 9187 |  | 12000 | 3444 | 9187
| Males - Males |  |  | 2250 | [8 empty] | 60 | 60 |  |  | 60 |  |  | 60 |  | 0 | 60 |  | 189 | 249 |  | 357 | 606 |  | 1602 | 2208 |  | 745 | 2953 |  |  | 2953 |  | 5005 |  | 6000 | 2052 | 5005
| Females - Females |  |  | 2750 | [8 empty] | 40 | 40 |  |  | 40 |  |  | 40 |  | 0 | 40 |  | 212 | 252 |  | 245 | 497 |  | 1596 | 2093 |  | 697 | 2790 |  |  | 2790 |  | 4182 |  | 6000 | 1392 | 4182
| Young - Young people | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  |  | 0
| Women in leadership position - Females | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 253 | 253 |  |  | 253 |  | 279 |  |  | 26 | 279
| 1.1.4 Persons trained in production practices and/or technologies | [42 empty] | 0
| Men trained in crop - Males |  |  | 1250 | [8 empty] | 1250 | 1250 |  | 1758 | 3008 | 5000 | 1522 | 4530 | 5000 | 1459 | 5989 | 5000 | 629 | 6618 | 5000 | 501 | 7119 |  | 0 | 7119 | 12 | 8 | 7127 |  |  | 12016 |  | 7139 |  |  | 12 | 7139
| Women trained in crop - Females |  |  | 781 | [8 empty] | 781 | 781 |  | 1546 | 2327 | 5000 | 1603 | 3930 | 5000 | 2264 | 6194 | 5000 | 744 | 6938 | 5000 | 551 | 7489 |  | 0 | 7489 | 8 | 4 | 7493 |  |  | 9988 |  | 7513 |  |  | 20 | 7513
| Men trained in livestock - Males |  |  | 1100 | [8 empty] | 598 | 598 |  | 1017 | 1615 |  | 1055 | 2670 | 1000 | 905 | 3575 | 1000 | 153 | 3728 | 1000 | 499 | 4227 |  | 245 | 4472 |  | 8 | 4480 |  |  | 6750 |  | 4519 |  | 38 | 39 | 4519
| Women trained in livestock - Females |  |  | 653 | [8 empty] | 520 | 520 |  | 1018 | 1538 |  | 606 | 2144 | 1000 | 999 | 3143 | 1000 | 200 | 3343 | 1000 | 498 | 3841 |  | 244 | 4085 |  | 4 | 4089 |  |  | 6439 |  | 4123 |  | 69 | 34 | 4123
| Young people trained in livestock - Young people | [12 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 12 | 12 |  |  | 12 |  | 18 |  |  | 6 | 18
| Total persons trained in crop - Number of people |  |  | 2031 | [8 empty] | 2031 | 2031 |  | 3304 | 5335 | 10000 | 3125 | 8460 | 10000 | 3723 | 12183 | 10000 | 1373 | 13556 | 10000 | 1052 | 14608 |  | 0 | 14608 | 20 | 12 | 14620 |  |  | 22004 |  | 14652 |  |  | 32 | 14652
| Total persons trained in livestock - Number of people |  |  | 1753 | [8 empty] | 1118 | 1118 |  | 2035 | 3153 |  | 1661 | 4814 | 2000 | 1904 | 6718 | 2000 | 353 | 7071 | 2000 | 997 | 8068 |  | 489 | 8557 |  | 12 | 8569 |  |  | 13189 |  | 8642 |  |  | 73 | 8642
| 2.1.3 Rural producers’ organizations supported |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Total size of POs - Organizations |  |  | 5000 | [14 empty] | 8933 | 8933 |  | 6065 | 14998 |  | 251 | 15249 |  | 602 | 15851 |  | 540 | 4301 |  | 1442 | 5743 |  |  | 17833 |  | 9187 |  |  | 3444 | 9187
| Rural POs supported - Organizations |  |  | 200 | [7 empty] | 6 | 18 | 18 |  |  | 18 |  | 60 | 78 |  | 28 | 106 |  | 11 | 117 |  | 14 | 131 |  | 27 | 158 |  | 91 | 249 |  |  | 249 |  | 329 |  |  | 80 | 329
| Males - Males |  |  | 2250 | [14 empty] | 4177 | 4177 |  | 3043 | 7220 |  | 124 | 7344 |  | 357 | 7701 |  | 270 | 2208 |  | 745 | 2953 |  |  | 8716 |  | 4345 |  |  | 2052 | 5005
| Females - Females |  |  | 2250 | [14 empty] | 4756 | 4756 |  | 3022 | 7778 |  | 127 | 7905 |  | 245 | 8150 |  | 270 | 2093 |  | 697 | 2790 |  |  | 9117 |  | 4182 |  |  | 1392 | 4182
| Young - Young people | [23 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | [5 empty] | 0
| 2.1.6 Market, processing or storage facilities constructed or rehabilitated |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Total number of facilities - Facilities |  |  | 111 | [7 empty] | 10 | 11 | 11 | 18 | 15 | 26 | 30 | 21 | 47 |  | 21 | 68 |  | 10 | 78 | 4 | 6 | 84 | 2 | 2 | 86 | 5 | 13 | 99 |  |  | 88 |  | 115 |  |  | 16 | 115
| Market facilities constructed/rehabilitated - Facilities |  |  | 93 | [7 empty] | 10 | 11 | 11 | 18 | 15 | 26 | 30 | 21 | 47 |  | 20 | 67 |  | 4 | 71 | 2 | 2 | 73 |  | 0 | 73 | 4 | 12 | 85 |  |  | 74 |  | 88 |  |  | 3 | 88
| Processing facilities constructed/rehabilitated - Facilities |  |  | 6 | [17 empty] | 1 | 1 |  | 6 | 7 | 2 | 3 | 10 | 1 | 1 | 11 | 1 | 1 | 12 |  |  | 12 |  | 13 |  |  | 1 | 13
| Storage facilities constructed/rehabilitated - Facilities |  |  | 12 | [20 empty] | 0 | 0 |  | 1 | 1 | 1 | 1 | 2 |  | 0 | 2 |  |  | 2 |  | 14 |  |  | 12 | 14
| 1.1.2 Farmland under water-related infrastructure constructed/rehabilitated |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Hectares of land - Area (ha) |  |  | 1922 | [7 empty] | 104 | 22 | 22 | 171 | 350 | 372 | 171 | 199 | 571 |  | 451.3 | 1022.3 |  | 200 | 1222.3 |  | 76.25 | 1298.55 | 100 | 95.1 | 1393.65 | 899.96 | 447 | 1840.65 |  |  | 1840.65 |  | 1898.25 |  |  | 57.6 | 1898.25
| 3.1.4 Land brought under climate-resilient practices |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Hectares of land - Area (ha) |  |  | 3000 | [7 empty] | 25 | 52 | 52 |  | 0 | 52 |  | 0 | 52 |  | 128.1 | 180.1 |  | 247.2 | 427.3 |  | 152.35 | 579.65 | 150 | 169.38 | 1316.91 | 47.67 | 1627 | 2943.91 |  |  | 776.59 |  | 3242.71 |  |  | 298.8 | 3242.71
Output Community-driven Strategic Market Infrastructure developed | Vegetable and dairy value chain processing and marketing infrastructure designed and constructed in 10 dzongkhags |  |  |  | Programme progress report - Sector reports and studies |  |  | Complementary financing from RGoB and FCBL will be provided as earmarked | [35 empty] | 0
| No. of value chain processing and market infrastructure - Number |  | 53 | [18 empty] | 20 | 20 |  | 0 | 20 |  |  | 21 |  | 0 | 21 |  | 0 | 21 |  |  |  |  | 115 |  |  | 94 | 115
Outcome Strengthened Agricultural Institutions and Policies for Improved and Resilient Agricultural and Marketing Practices | ≥ 70% of VC stakeholders report the use of market information in investment decision-making 60% of VC stakeholders report satisfaction with the policy and regulatory framework as providing a fair distribution of incentives, costs, benefits, and risks |  |  |  | Programme M&E reports - Line agencies’ - Department of Agriculture Marketing and Cooperatives (DAMC), FCBL and Business Opportunity and Information Centre (BOiC) reports - Sector studies and reports - Programme survey |  |  | MoAF will pro-actively implement the 11th FYP strategy for enabling private sector engagement and participation within the process of commercialisation of agricultural development | [35 empty] | 0
| % of stakeholders reporting use of market information - Percentage (%) | 15 | 30 | 70 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
| 3.2.2 Households reporting adoption of environmentally sustainable and climate-resilient technologies and practices |  |  |  | RIMS | Annual | [37 empty] | 0
| Households - Percentage (%) |  | 58 | [21 empty] | 0 | 0 |  | 39.44 | 39.44 |  | 0 | 39.44 |  |  | 39.44 |  |  |  |  | 39.44 |  |  |  | 39.44
| Women-headed households - Households |  | 1260 | [9 empty] | 236.16 |  |  | 2469 |  |  | 1620 | 0 |  | 177 | 0 |  | 432 | 0 |  | 428 | 0 |  | 2680 | 0 |  | 841 | 0 |  |  |  |  | 572 |  |  | 572 | 572
| Households - Households |  | 3107 | 20283 | [8 empty] | 492 | 492 | 10000 | 5144 | 5636 | 10000 | 3375 | 9011 |  | 370 | 9381 |  | 900 | 10281 |  | 892 | 11173 |  | 5584 | 16757 | 2601 | 1753 | 18510 |  |  |  |  | 19707 |  |  | 1197 | 19707
| 3.2.3 Households reporting a significant reduction in the time spent for collecting water or fuel |  |  |  | RIMS | Annual | [37 empty] | 0
| Households - Households |  | 1700 | 8693 | [20 empty] | 265 | 265 |  | 338 | 603 |  | 190 | 793 |  | 202 | 2478 | [8 empty] | 2478
| Households - Percentage (%) |  | 20 | 30 | [39 empty] | 0 |  |  |  |  | To be reported after end-line survey
| Women-headed households - Households | [23 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2492 | 783 | 783 | [8 empty] | 783
| 1.2.3 Households reporting reduced water shortage vis-à-vis production needs | [42 empty] | 0
| Households - Percentage (%) | [32 empty] | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | End-line survey
| Households - Households | [23 empty] | 1075 | 1075 |  | 363 | 1438 |  | 266 | 1704 | 1081 | 899 | 2603 |  |  |  |  | 2603 |  |  |  | 2603
| Total number of household members - Number of people | [23 empty] | 3762 | 3762 |  | 2000 | 5762 |  | 1054 | 6816 |  | 3596 | 10412 |  |  |  |  | 10412 |  |  |  | 10412
| Poor smallholder household members supported in coping with the effects of climate change |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Females - Females |  |  | 57500 | [8 empty] | 560 | 560 |  |  | 560 |  | 160 | 720 |  | 3116 | 3836 |  | 661 | 4497 |  | 179 | 4676 |  | 198 | 66580 |  | 4000 | 70580 |  |  |  |  | 72763 |  | 3140 | 2183 | 72763
| Males - Males |  |  | 57500 | [8 empty] | 925 | 925 |  | 357 | 1282 |  | 160 | 1442 |  | 2407 | 3849 |  | 554 | 4403 |  | 201 | 4604 |  | 198 | 65385 |  | 3616 | 69001 |  |  |  |  | 71475 |  | 3513 | 2474 | 71475
| Total household members - Number of people |  |  | 115000 | [8 empty] | 1485 | 1485 |  | 357 | 1842 |  | 320 | 2162 |  | 5523 | 7685 |  | 1215 | 8900 |  | 380 | 9280 |  | 396 | 131965 |  | 7616 | 139581 |  |  |  |  | 144238 |  | 6653 | 4657 | 144238
| Households supported with increased water availability or efficiency |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Households - Households |  |  | 10000 | [11 empty] | 1919 | 1919 |  | 1267 | 3186 |  | 522 | 3708 |  | 1876 | 5584 |  | 1876 | 7460 |  | 266 | 7726 | 1081 | 899 | 8625 |  |  |  |  | 8916 |  |  | 291 | 8916
| Individuals engaged in NRM and climate risk management activities |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Males - Males |  |  | 15000 | [20 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 15371 |  |  |  |  | 16988 |  |  | 1617 | 16988
| Total - Number of people |  |  | 30000 | [14 empty] | 820 | 820 |  | 3894 | 4714 |  | 2435 | 7149 |  | 5416 | 12565 |  | 725 | 13290 | 1326 | 1185 | 29546 |  |  |  |  | 33003 |  |  | 3457 | 33003
| Females - Females |  |  | 15000 | [20 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 14175 |  |  |  |  | 16015 |  |  | 1840 | 16015
| Community groups engaged in NRM and climate risk management activities |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Groups - Groups |  |  | 65 | [20 empty] | 0 |  |  | 0 | 0 |  | 158 | 158 |  | 91 | 249 |  |  |  |  | 329 |  |  | 80 | 329
| Group members - females - Females |  |  | 2750 | [20 empty] | 0 |  |  | 0 | 0 |  | 2093 | 2093 |  | 697 | 2790 |  |  |  |  | 4182 |  |  | 1392 | 4182
| Group members - males - Males |  |  | 2250 | [20 empty] | 0 |  |  | 0 | 0 |  | 2208 | 2208 |  | 745 | 2953 |  |  |  |  | 5005 |  |  | 2052 | 5005
| Group members - total - Number of people |  |  | 5000 | [20 empty] | 0 |  |  | 0 | 0 |  | 4301 | 4301 |  | 1442 | 5743 |  |  |  |  | 9187 |  |  |  | 5743
Output Strengthened value chain and marketing knowledge and communication | Market Information System MoAF/DAMC providing relevant (real-time) information to farmers |  |  |  | Programme M&E reports Line agencies’, DAMC, FCBL and BOiC reports Sector studies and reports |  |  | Adequate technical and process support is provided to develop the models and approaches on the ground, to access learning and to document good practice (presently a weak part of IFAD projects) | [35 empty] | 0
| No of market information system - Number |  |  | 5 | [14 empty] | 1 | 1 |  |  | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  |  |  |  | 1 |  |  |  | 1
| 2.1.2 Persons trained in income-generating activities or business management |  |  |  | RIMS | Annual | OPM | [36 empty] | 0
| Males - Males |  | 486 | [9 empty] | 60 | 60 |  | 465 | 525 |  | 864 | 1389 |  | 891 | 2280 |  | 2284 | 4564 |  | 0 | 4564 |  | 0 | 4564 |  | 0 | 4564 |  |  | 4564 |  | 4604 |  |  | 40 | 4604
| Females - Females |  | 324 | [9 empty] | 40 | 40 |  | 746 | 786 |  | 576 | 1362 |  | 1029 | 2391 |  | 2431 | 4822 |  | 0 | 4822 |  | 0 | 4822 |  | 0 | 4822 |  |  | 4822 |  | 4856 |  |  | 34 | 4856
| Persons trained in IGAs or BM (total) - Number of people |  | 810 | 9671 | [8 empty] | 100 | 100 |  | 1211 | 1311 |  | 1440 | 2751 |  | 1920 | 4671 |  | 4715 | 9386 |  | 0 | 9386 |  | 0 | 9386 |  | 0 | 9386 |  |  | 9386 |  | 9460 |  |  | 74 | 9460
Output Climate change resilience and value chain development lessons mainstreamed in agricultural policies and sector strategies | Enhanced engineering norms for building climate resilient irrigation systems |  |  |  | Programme M&E reports Line agencies’ reports Sector studies and reports Policy documents Regulatory framework document for private sector and PPP |  |  | Dialogue and collaboration between Government Agencies/staff and external stakeholders is successful and generates meaningful lessons and insights for policy development | [35 empty] | 0
| No. of norms - Number |  |  | 1 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 1 |  |  | 1 | 1
| Vegetable and dairy development policies enhanced based on multi-stakeholder consultation processes and programme lessons (resilience, value chain and marketing) |  |  |  | Programme M&E reports Line agencies’ reports Sector studies and reports Policy documents Regulatory framework document for private sector and PPP | [38 empty] | 0
| No. of policies - Number |  |  | 1 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 1 |  |  | 1 | 1
| Regulatory framework for private sector development and PPP in agriculture sector developed |  |  |  | Programme M&E reports Line agencies’ reports Sector studies and reports Policy documents Regulatory framework document for private sector and PPP | [38 empty] | 0
| No. of framework - Number |  |  | 1 | [20 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
| 3.1.2 Persons provided with climate information services |  |  |  | RIMS | Annual | [37 empty] | 0
| Males - Males |  |  | 2500 | [11 empty] | 6 | 6 |  |  | 6 |  | 358 | 364 |  | 66 | 430 |  | 169 | 599 |  | 95 | 694 |  | 0 | 694 |  |  | 694 |  | 694 |  |  |  | 694
| Females - Females |  |  | 2500 | [11 empty] | 86 | 86 |  |  | 86 |  | 540 | 626 |  | 88 | 714 |  | 154 | 868 |  | 95 | 963 |  | 0 | 963 |  |  | 963 |  | 963 |  |  |  | 963
| Young - Young people | [14 empty] | 90 | 90 |  |  | 90 |  | 46 | 136 |  | 10 | 146 |  | 0 | 146 |  | 0 | 146 |  | 0 | 146 |  |  | 146 |  | 146 |  |  |  | 146
| Persons provided with climate information services - Number of people |  |  | 5000 | [11 empty] | 92 | 92 |  |  | 92 |  | 898 | 990 |  | 154 | 1144 |  | 323 | 1467 |  | 190 | 1657 |  | 0 | 1657 |  |  | 1657 |  | 1657 |  |  |  | 1657
| 1.1.3 Rural producers accessing production inputs and/or technological packages |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Males - Males | [11 empty] | 556 | 556 |  | 4177 | 4733 |  | 286 | 5019 |  | 3043 | 8062 |  | 3318 | 11380 |  | 4990 | 16370 |  | 2462 | 14371 | 5724 | 1000 | 15371 |  |  | 22011 |  | 16988 |  |  | 1617 | 16988
| Females - Females | [11 empty] | 260 | 260 |  | 4756 | 5016 |  | 110 | 5126 |  | 3022 | 8148 |  | 2632 | 10780 |  | 6351 | 17131 |  | 2847 | 13271 | 4625 | 904 | 14175 |  |  | 22718 |  | 16015 |  |  | 1840 | 16015
| Young - Young people | [23 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | [5 empty] | 0
| Total rural producers - Number of people | [11 empty] | 816 | 816 |  | 8933 | 9749 |  | 396 | 10145 |  | 6065 | 16210 |  | 5950 | 22160 |  | 11341 | 33501 |  | 5309 | 27642 | 10349 | 1904 | 44729 |  |  | 44729 |  | 33003 |  |  | 3457 | 48186
| 1.1.2 Farmland under water-related infrastructure constructed/rehabilitated |  |  |  | RIMS | Annual | [37 empty] | 0
| Hectares of land - Area (ha) |  |  | 1922 | [8 empty] | 22 | 22 | 171 | 350 | 372 |  | 0 | 372 |  | 151 | 523 |  | 332 | 855 | 360 | 169.23 | 1024.23 |  | 95.1 | 1228.39 | 899.96 | 447 | 1675.39 |  |  | 1675.39 |  | 1732.99 |  |  | 57.6 | 1732.99
| 3.1.3 Persons accessing technologies that sequester carbon or reduce greenhouse gas emissions |  |  |  | RIMS | Annua | [37 empty] | 0
| Males - Males |  |  | 2500 | [11 empty] | 12 | 12 |  | 260 | 272 |  | 122 | 394 |  | 80 | 474 |  | 100 | 574 |  | 120 | 694 | 12 | 20 | 714 |  |  | 714 |  | 1598 |  |  | 884 | 1598
| Females - Females |  |  | 2500 | [11 empty] | 0 | 0 |  | 360 | 360 |  | 78 | 438 |  | 80 | 518 |  | 96 | 614 |  | 70 | 684 | 28 | 11 | 695 |  |  | 695 |  | 2110 |  |  | 1415 | 2110
| Young - Young people | [23 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  |  | 0
| Total persons accessing technologies - Number of people |  |  | 5000 | [11 empty] | 12 | 12 |  | 620 | 632 |  | 200 | 832 |  | 160 | 992 |  | 196 | 1188 |  | 190 | 1378 | 40 | 31 | 1409 |  |  | 1409 |  | 3708 |  |  | 2299 | 3708
| Government officials and staff trained | [42 empty] | 0
| Males - Number |  |  | 180 | [8 empty] | 5 | 5 |  | 59 | 64 |  | 12 | 76 |  | 68 | 144 |  | 31 | 174 | 15 | 0 | 174 |  | 0 | 174 |  | 19 | 193 |  |  |  |  | 291 |  |  | 98 | 291
| Females - Number |  |  | 80 | [11 empty] | 15 | 15 |  | 3 | 18 |  | 11 | 29 |  | 7 | 36 | 15 | 0 | 36 |  | 0 | 36 |  | 2 | 38 |  |  |  |  | 61 |  |  | 23 | 61
| 2.1.1 Rural enterprises accessing business development services |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Rural enterprises - Enterprises |  |  | 256 | [17 empty] | 0 | 0 |  | 188 | 188 |  | 8 | 196 |  | 0 | 196 |  | 10 | 206 |  |  | 206 |  | 212 |  |  | 6 | 212 |  |  |  | 82.8125
| Number of groups supported to sustainably manage natural resources and climate-related risks | [42 empty] | 0
| Number of groups supported by crops sector - Number | [11 empty] | 8 | 8 |  | 75 | 83 |  | 5 | 88 |  | 6 | 94 |  | 0 | 94 |  | 0 | 94 |  | 14 | 108 |  | 10 | 118 |  |  |  |  | 118 |  |  |  | 118
| Number of groups supported by livestock sector - Number | [14 empty] | 32 | 32 |  | 81 | 113 |  | 6 | 119 |  | 0 | 119 |  | 0 | 119 |  | 7 | 126 |  | 12 | 138 |  |  |  |  | 138 |  |  |  | 138
| Natural resource manage groups with women in leadership positions - Number | [15 empty] | 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
| Number of members of the project-supported enterprise | [42 empty] | 0
| Males - Number | [11 empty] | 25 | 25 |  |  | 25 |  | 5 | 30 |  | 50 | 80 |  | 0 | 80 |  | 0 | 80 |  | 12 | 92 |  | 18 | 110 |  |  |  |  | 114 |  |  | 4 | 114
| Females - Number | [11 empty] | 45 | 45 |  |  | 45 |  | 81 | 126 |  | 23 | 149 |  | 0 | 149 |  | 0 | 149 |  | 7 | 156 |  | 12 | 168 |  |  |  |  | 176 |  |  | 8 | 176
| Young - Number | [11 empty] | 25 | 25 |  |  | 25 |  | 5 | 30 |  |  | 30 |  | 0 | 30 |  | 0 | 30 |  | 2 | 32 |  | 0 | 32 |  |  |  |  | 32 |  |  |  | 32
| Number of project-supported enterprise with women in leadership positions - Number | [11 empty] | 22 | 22 |  |  | 22 |  | 3 | 25 |  | 5 | 30 |  | 0 | 30 |  | 0 | 30 |  | 7 | 37 |  | 0 | 37 |  |  |  |  | 39 |  |  | 2 | 39
| Number of project-supported enterprise headed by young farmers - Number | [11 empty] | 3 | 3 |  |  | 3 |  | 6 | 9 |  | 5 | 14 |  | 0 | 14 |  | 0 | 14 |  | 10 | 24 |  | 0 | 24 |  |  |  |  | 29 |  |  | 5 | 29
| International and country dialogues on climate supported |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Dialogues - Number |  |  | 1 | [20 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 1 | 1 |  |  |  |  | 1 |  |  |  | 1
| Land under climate-resilient practices |  |  |  | RIMS | Annual | PMU | [36 empty] | 0
| Land area - Area (ha) |  |  | 3000 | [10 empty] | 148 | 619 | 619 |  | 92 | 711 |  | 65 | 776 |  | 184.4 | 184.4 |  | 152.35 | 1112.75 |  | 1627 | 2943.91 |  | 27.56 | 2971.47 |  |  |  |  | 3173.47 |  |  | 202 | 3173.47
Note on B95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Disaggregator HH members missing
Note on B109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Disaggregator number of HH missing. If project has results please add
Note on B111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Disaggregator number of HH members and females/males missing. If project has results, please add
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Missing target?
Note on E62: Target revised from 3337 to 5000
Note on E63: Target revised
Note on E64: Target revised
Note on E76: Target revised from 25000 to 5000
Note on E89: Target revised from 730 to 3000 Ha in 2024
Note on E117: Target revised from 65 to 200 in 2024
Note on N73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not possible if higher that outreach
Note on T73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Higher than outreach?
Note on Z15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Higher than HH members? Also, where does this number come from (it seems that output results are lower)?
Note on Z41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assessed but 0?
Note on AC31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Higher than outreach HHs
Note on AF15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where does this number come from (it seems that output results are lower)?
Note on AF27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ration HH/HH members is off range: 2 Average household size is 4.6 members per HH
Note on AI31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Higher than outreach HHs
Note on AJ83: Vegetable shed Sale counter outlet roadside market sheds
Note on AJ85: Collection shed and collection center
Note on AR6: USER: Average household size of 4 members as per BLSS 2022
Note on AR52: membership in 6 WUA
Note on AR55: 6 WUA and 4 MCC's
Note on AR57: 3 groups in 4 dzongkhags strengthened through training and 2 new groups formed
Note on AR87: USER: 48 households benefited from irrigation canal construction/renovation. Average land size of 1.2 Ha considered for land area estimation
Note on AR89: USER: 249 hh supported with climate resilient agricultural practices. Average land of 1.2 Ha considered for estimation
Note on AR130: Role of aggregators not reported earlier and establishment of EAMC through MSP and B2B linkages
Note on AR149: USER: Biogas installation